## 01_Cover_Summary
DDO++ Attendance — Server Deploy & Local Scheduler
Project plan · 15 working days · Thu 10 Sep 2026 to Wed 30 Sep 2026 · Prepared 9 Sep 2026
Document Control
Field | Value
Document Name | Attendance Go-Live Plan
Programme | DDO++ Attendance Module
Plan Start Date | 10-Sep-2026
Plan Finish Date | 30-Sep-2026
Target Go-Live Date | 30-Sep-2026
Hypercare Window | 30-Sep-2026 to 02-Oct-2026
Working Days | 15
Sites in Scope | Noida, Agra, Hyderabad
Primary Delivery Model | 1 developer FTE + part-time Infra and HR
Central Component | attendance_api.js on shared server (HTTPS + PostgreSQL)
Local Component | attendance_import.js via Windows Task Scheduler
Out of Scope | Auto-export from biometric machine; NocoBase UI replacement
Document Owner | Project Manager
Status | Baseline for Day-1 kickoff
Plan Snapshot
Workstream | Objective | Window | Success Measure
A — Central Server | Run attendance API as a managed HTTPS service writing to NocoBase PostgreSQL | 10–16 Sep 2026 | /health and import succeed from an office PC over HTTPS
B — Local Scheduler | Office inbox drop auto-imports every 10 minutes without a manual command | 17–25 Sep 2026 | Noida real file appears on dashboard within 10 minutes of drop
C — Rollout & UAT | Agra + Hyderabad agents live; scheduled import matches last manual file | 24–30 Sep 2026 | Go / No-Go signed on 29 Sep; cutover 30 Sep
Day-1 Decisions (must lock 10 Sep)
Decision ID | Topic | Recommended Option | Rejected Option | Rationale
DEC-01 | Office importer runtime | Node attendance_import.js | Python importer_script.py as production agent | Node agent already has inbox / processed / failed / logs; one runtime with the API
DEC-02 | Local trigger | Windows Task Scheduler every 10 minutes, 08:00–20:00 IST, Mon–Sat | Long-running file-watcher Windows service | Survives reboot; office IT can support; no extra service to babysit
DEC-03 | API hosting | Sidecar on the same host as NocoBase PostgreSQL | Separate database or JSON-file store | Dockerfile already exists; avoids a second source of truth

## 02_Master_Task_Register
Master Task Register
All delivery tasks · filter by Workstream, Owner Role, Status, or Site / Location
Task ID | Workstream | Phase | Task Name | Description | Owner Role | Support Role | Start Date | Finish Date | Duration (Hours) | Predecessor Task ID | Priority | Status | Site / Location | Acceptance Criteria | Notes
A0.1 | A — Central Server | Kickoff | Kickoff and freeze delivery decisions | Confirm server OS/host, Postgres access, three office PCs, who drops Excel, and import cadence. | Project Manager | Dev, Infra, HR | 10-Sep-2026 | 10-Sep-2026 | 8 | — | Critical | Not Started | All sites | Host, token owner, folder path, and 10-minute cadence signed | Day-1 gate
A1.1 | A — Central Server | API Hardening | Bind API beyond localhost and place reverse proxy | Listen on 0.0.0.0 or Unix socket; Nginx/IIS in front of attendance_api.js. | Developer | Infra | 11-Sep-2026 | 11-Sep-2026 | 3 | A0.1 | Critical | Not Started | Central server | curl from another machine hits /health | Currently bound to 127.0.0.1:3000
A1.2 | A — Central Server | API Hardening | Enable TLS and HTTP to HTTPS redirect | Install certificates; keep HTTP only on localhost. | Infra | Developer | 15-Sep-2026 | 15-Sep-2026 | 3 | A1.1 | Critical | Not Started | Central server | Importer POST succeeds on https://<host>/api/attendance/import | Blocks office scheduler
A1.3 | A — Central Server | API Hardening | Rotate production API token | Replace POC token; store DDO_API_TOKEN in server env/secrets only. | Developer | Infra | 11-Sep-2026 | 14-Sep-2026 | 1 | A1.1 | High | Not Started | Central server | Old token returns 401; new token is not in source control | POC value is dev-ddo-attendance-token
A1.4 | A — Central Server | API Hardening | Require PostgreSQL in production | Refuse JSON-file fallback when NODE_ENV=production; require DATABASE_URL. | Developer | Infra | 11-Sep-2026 | 14-Sep-2026 | 2 | A0.1 | High | Not Started | Central server | Missing DB env causes non-zero exit | Must share NocoBase database
A1.5 | A — Central Server | API Hardening | Structured logs, rotation, and health check | Stdout + file logs; unauthenticated /health for load balancer; process manager restart. | Developer | Infra | 14-Sep-2026 | 14-Sep-2026 | 2 | A1.1 | High | Not Started | Central server | Crash auto-restarts; /health is 200 | PM2, systemd, or NSSM
A1.6 | A — Central Server | API Hardening | Allow-list office IPs or VPN on import POST | Restrict POST /api/attendance/import to office networks. | Infra | Developer | 15-Sep-2026 | 15-Sep-2026 | 2 | A1.2 | High | Not Started | Central server | Non-office IP is rejected at proxy or app | Noida, Agra, Hyd egress IPs needed
A1.7 | A — Central Server | API Hardening | Smoke import of last Noida batch | Replay last successful Noida file; confirm UPSERT does not duplicate rows. | Developer | HR | 16-Sep-2026 | 16-Sep-2026 | 3 | A1.4 | High | Not Started | Noida | Dashboard counts match POC; re-import updates only | Use existing output batch as reference
A2.1 | A — Central Server | Host Deploy | Provision VM or reuse NocoBase host | Node 18+, git, firewall port 443, SSH access. | Infra | Developer | 14-Sep-2026 | 14-Sep-2026 | 3 | A0.1 | Critical | Not Started | Central server | SSH in; node -v is 18 or higher | Prefer same host as Postgres
A2.2 | A — Central Server | Host Deploy | Deploy API via Docker/compose or PM2/systemd | Do not use a manual npm start session as the run model. | Developer | Infra | 14-Sep-2026 | 14-Sep-2026 | 3 | A2.1 | Critical | Not Started | Central server | Service starts on boot | Dockerfile already in repo
A2.3 | A — Central Server | Host Deploy | Connect NocoBase Postgres and apply schema | Apply schema/postgres_baseline.sql; confirm att_* tables. | Developer | Infra | 14-Sep-2026 | 15-Sep-2026 | 2 | A2.2 | Critical | Not Started | Central server | API log says PostgreSQL store | Same DB as NocoBase 0.9
A2.4 | A — Central Server | Host Deploy | Nightly backup of att_* and restore drill | pg_dump of attendance tables; restore once onto a copy database. | Infra | Developer | 15-Sep-2026 | 16-Sep-2026 | 2 | A2.3 | High | Not Started | Central server | Restore tested on a copy database | Include in go-live evidence
A2.5 | A — Central Server | Host Deploy | Write one-page server runbook | Start/stop, logs, token rotate, rollback git tag. | Developer | Infra | 16-Sep-2026 | 16-Sep-2026 | 2 | A2.2 | Medium | Not Started | Central server | Infra can restart without the developer on the call | Keep to one page
A3.1 | A — Central Server | Server Acceptance | Server acceptance pack | Run /health, UI, POST import, Postgres persist, and idempotency checks. | Developer | Infra, HR | 16-Sep-2026 | 16-Sep-2026 | 4 | A1.7, A2.4 | Critical | Not Started | Central server | All five server checks pass (see Server_Acceptance sheet) | Hard gate before Noida pilot
B1.1 | B — Local Scheduler | Agent Behaviour | Empty inbox exits success (code 0) | Task Scheduler must not mark the job failed when inbox is empty. | Developer | Office IT | 16-Sep-2026 | 17-Sep-2026 | 1 | A0.1 | Critical | Not Started | All sites | No files → log INFO, exit 0 | Current importer exits 1 on empty input/
B1.2 | B — Local Scheduler | Agent Behaviour | Ignore temp Excel locks and in-copy files | Skip ~$*.xls and files still being written. | Developer | — | 17-Sep-2026 | 17-Sep-2026 | 2 | B1.1 | High | Not Started | All sites | Open/saving file is skipped until next 10-minute tick | Common HR failure mode
B1.3 | B — Local Scheduler | Agent Behaviour | Single-instance lock file | Prevent two Task Scheduler ticks importing the same report. | Developer | — | 17-Sep-2026 | 17-Sep-2026 | 2 | B1.1 | High | Not Started | All sites | Second process exits 0 with already running | Required for 10-minute cadence
B1.4 | B — Local Scheduler | Agent Behaviour | Skip already-processed content by file hash | Re-drop of same file is UPSERT/log, not a crash. | Developer | — | 18-Sep-2026 | 18-Sep-2026 | 2 | B1.3 | Medium | Not Started | All sites | Same file twice logged as duplicate or update | API already UPSERTs by employee+date
B1.5 | B — Local Scheduler | Agent Behaviour | PowerShell wrapper and last-run stamp | scheduler.ps1 selects files, uses LOCATION_CODE, writes last-run timestamp. | Developer | Office IT | 17-Sep-2026 | 18-Sep-2026 | 3 | B1.1 | High | Not Started | All sites | IT can run scheduler.ps1 by hand and see a one-line result | Registered in Task Scheduler
B1.6 | B — Local Scheduler | Agent Behaviour | Failure alert when failed folder or API down | Log plus optional SMTP/Teams webhook within one tick. | Developer | Infra | 18-Sep-2026 | 18-Sep-2026 | 2 | B1.5 | High | Not Started | All sites | Forced API-down test is visible within 10 minutes | Do not email on empty inbox
B2.1 | B — Local Scheduler | Package & Pilot | Build office install package and HR card | Zip: Node note, .env.example, Task Scheduler XML, one-page HR drop-folder card. | Developer | Office IT | 21-Sep-2026 | 21-Sep-2026 | 3 | B1.6 | High | Not Started | All sites | A non-developer follows the card and completes a dry run | Python script excluded from zip
B2.2 | B — Local Scheduler | Package & Pilot | Install Noida agent | LOCATION_CODE=NOIDA; DDO_API_ENDPOINT = production HTTPS URL. | Office IT | Developer, HR | 22-Sep-2026 | 22-Sep-2026 | 3 | A3.1, B2.1 | Critical | Not Started | Noida | Test drop appears on server dashboard within 10 minutes | Pilot site
B2.3 | B — Local Scheduler | Package & Pilot | Noida soak with real file and re-import | One real monthly/weekly file plus re-import UPSERT check. | HR | Developer | 23-Sep-2026 | 23-Sep-2026 | 4 | B2.2 | Critical | Not Started | Noida | HR confirms counts; no duplicate employees | Do not skip soak if crashing the timeline
B2.4 | B — Local Scheduler | Package & Pilot | Train one HR user on drop and failure folder | User completes a drop without development in the room. | HR | Office IT | 23-Sep-2026 | 23-Sep-2026 | 2 | B2.2 | High | Not Started | Noida | User finds failed/ without calling development | Repeat at Agra and Hyd
B3.1 | B — Local Scheduler | Site Rollout | Install Agra agent | Same package; LOCATION_CODE=AGRA. | Office IT | Developer, HR | 24-Sep-2026 | 24-Sep-2026 | 3 | B2.3 | High | Not Started | Agra | Agra file lands under Agra in All Locations view | Do not share a PC across offices
B3.2 | B — Local Scheduler | Site Rollout | Install Hyderabad agent | LOCATION_CODE=HYD; sample file acceptable if no live export yet. | Office IT | Developer, HR | 25-Sep-2026 | 25-Sep-2026 | 3 | B2.3 | Medium | Not Started | Hyderabad | Agent installed; sample or live file proves the path | Live data may follow later
C1.1 | C — Rollout & UAT | UAT & Cutover | Cross-site UAT versus last manual file | Compare scheduled import to last manual import; own unknown-employee list. | HR | Developer | 28-Sep-2026 | 28-Sep-2026 | 8 | B3.1, B3.2 | Critical | Not Started | All sites | Exception list assigned to named HR owner | Unknown codes already seen on Noida POC
C1.2 | C — Rollout & UAT | UAT & Cutover | Go-live rehearsal and rollback drill | Disable Task Scheduler; roll API to previous git tag once. | Project Manager | Dev, Infra | 29-Sep-2026 | 29-Sep-2026 | 8 | C1.1 | Critical | Not Started | All sites | Written go / no-go on 29 Sep | No-go slips to next working day
C1.3 | C — Rollout & UAT | UAT & Cutover | Cutover and hypercare day 1 | Production live; same-day response on failed/ folders through 2 Oct. | Project Manager | Dev, HR, Infra | 30-Sep-2026 | 30-Sep-2026 | 8 | C1.2 | Critical | Not Started | All sites | Live traffic on scheduled path; hypercare roster named | Hypercare 30 Sep–2 Oct

## 03_Delivery_Calendar
Delivery Calendar
10 Sep 2026 – 30 Sep 2026 · IST · weekends off · 15 working days
Day Number | Calendar Date | Day of Week | Working Day (Y/N) | Focus Area | Workstream | Planned Output | Planned Hours | Primary Owner | Support Roles | Milestone (Y/N)
D1 | 10-Sep-2026 | Thursday | Y | Kickoff and freeze decisions | A + B | Host, token owner, folder path, cadence signed | 8 | Project Manager | Dev, Infra, HR | Y
D2 | 11-Sep-2026 | Friday | Y | API bind, token, refuse JSON in prod | A — Central Server | Hardened build on a branch | 8 | Developer | Infra | N
— | 12-Sep-2026 | Saturday | N | Non-working | — | — | 0 | — | — | N
— | 13-Sep-2026 | Sunday | N | Non-working | — | — | 0 | — | — | N
D3 | 14-Sep-2026 | Monday | Y | Server provision and first deploy | A — Central Server | API up on host; /health green | 8 | Infra | Developer | Y
D4 | 15-Sep-2026 | Tuesday | Y | TLS, firewall, database backups | A — Central Server | HTTPS import from a non-local client | 8 | Infra | Developer | Y
D5 | 16-Sep-2026 | Wednesday | Y | Server UAT, runbook, start agent lock/empty-inbox | A then B | Server accepted; scheduler design locked | 8 | Developer | Infra, HR | Y
D6 | 17-Sep-2026 | Thursday | Y | Wrapper, lock, skip temp Excel files | B — Local Scheduler | scheduler.ps1 works locally | 8 | Developer | Office IT | N
D7 | 18-Sep-2026 | Friday | Y | Hash skip and failure alert | B — Local Scheduler | Forced-fail test visible in failed/ | 8 | Developer | Infra | N
— | 19-Sep-2026 | Saturday | N | Non-working | — | — | 0 | — | — | N
— | 20-Sep-2026 | Sunday | N | Non-working | — | — | 0 | — | — | N
D8 | 21-Sep-2026 | Monday | Y | Package and install card | B — Local Scheduler | Drop-in zip for office IT | 8 | Developer | Office IT | N
D9 | 22-Sep-2026 | Tuesday | Y | Noida pilot install | B — Local Scheduler | First scheduled import in production DB | 8 | Office IT | Developer, HR | Y
D10 | 23-Sep-2026 | Wednesday | Y | Noida soak and HR training | B — Local Scheduler | Pilot sign-off or punch-list | 8 | HR | Developer | Y
D11 | 24-Sep-2026 | Thursday | Y | Agra rollout | C — Rollout & UAT | Agra LOCATION_CODE live | 6 | Office IT | Developer, HR | N
D12 | 25-Sep-2026 | Friday | Y | Hyderabad rollout | C — Rollout & UAT | Three agents installed | 6 | Office IT | Developer, HR | N
— | 26-Sep-2026 | Saturday | N | Non-working / optional soak | B — Local Scheduler | Leave Noida job running | 0 | — | — | N
— | 27-Sep-2026 | Sunday | N | Non-working / optional soak | B — Local Scheduler | Leave Noida job running | 0 | — | — | N
D13 | 28-Sep-2026 | Monday | Y | Cross-site UAT vs last manual file | C — Rollout & UAT | Unknown-employee list owned by HR | 8 | HR | Developer | Y
D14 | 29-Sep-2026 | Tuesday | Y | Go-live rehearsal and rollback drill | C — Rollout & UAT | Written go / no-go | 8 | Project Manager | Dev, Infra | Y
D15 | 30-Sep-2026 | Wednesday | Y | Cutover and hypercare day 1 | C — Rollout & UAT | Live; 3-day hypercare into 1–2 Oct | 8 | Project Manager | Dev, HR, Infra | Y

## 04_RAID_Log
RAID Log
Risks, Assumptions, Issues, Dependencies — review at kickoff and every Friday
RAID ID | Type | Title | Description | Likelihood | Impact | Risk Score | Mitigation / Response | Owner Role | Due Date | Status
R-01 | Risk | API still bound to localhost | Office schedulers appear to run but data never reaches the server. | High | High | High | Noida pilot is blocked until /health works from that PC. | Developer | 16-Sep-2026 | Open
R-02 | Risk | No route from office PC to server:443 | Site cannot import. | Medium | High | High | Day-1 network test; document VPN fallback. | Infra | 10-Sep-2026 | Open
R-03 | Risk | Excel file dropped while still open | Partial read lands in failed/. | High | Medium | High | Skip locked and ~$ files; next tick retries. | Developer | 17-Sep-2026 | Open
R-04 | Risk | Unknown employee codes | Rows skipped; HR thinks import failed. Already seen on Noida POC. | High | High | High | Dashboard exceptions plus HR master-data cleanup on D13. | HR | 28-Sep-2026 | Open
R-05 | Risk | Two importers confuse operators | Python and Node both exist; wrong script misses inbox. | Medium | Medium | Medium | Python labelled lab-only; offices receive Node zip only. | Project Manager | 21-Sep-2026 | Open
A-01 | Assumption | NocoBase Postgres reachable from API host | No persist if DATABASE_URL is wrong. | — | High | High | Confirm DATABASE_URL on D1; deploy sidecar on same host. | Infra | 10-Sep-2026 | Open
A-02 | Assumption | One LOCATION_CODE per machine | Wrong location tagging if a PC is shared across offices. | — | High | High | Do not share one PC across offices. | Office IT | 22-Sep-2026 | Open
D-01 | Dependency | TLS certificate and DNS name | Blocks D4 HTTPS work. | — | High | High | If public cert delayed, use internal CA — do not skip TLS on WAN. | Infra | 15-Sep-2026 | Open
D-02 | Dependency | Named HR owner for unknown employees | UAT cannot close. | — | High | High | Name an HR owner on D1. | Project Manager | 10-Sep-2026 | Open
D-03 | Dependency | Office egress IPs or VPN | Cannot complete import allow-list. | — | Medium | Medium | Collect Noida, Agra, Hyd public IPs during kickoff. | Infra | 10-Sep-2026 | Open

## 05_Go_Live_Checklist
Go-Live Checklist
Cut over on 30 Sep 2026 only if every row is Done · hypercare 30 Sep–2 Oct
Item No. | Category | Go-Live Criterion | Owner Role | Evidence Required | Status | Sign-off Date | Sign-off Name
GL-01 | Infrastructure | API /health and UI reachable over HTTPS from Noida, Agra, and Hyd PCs | Infra | Screenshot or curl log from each office PC | Pending
GL-02 | Security | Production token in use; POC token disabled | Developer | 401 response with old token; secrets store entry | Pending
GL-03 | Data | PostgreSQL is the store; JSON api_data is not used in production | Developer | API startup log line showing PostgreSQL store | Pending
GL-04 | Resilience | Restore drill of att_* completed once | Infra | Restore log on copy database | Pending
GL-05 | Functional | Noida scheduled import of a real file matches last manual import (UPSERT, not extra rows) | HR | Dashboard counts + batch summary | Pending
GL-06 | Rollout | Agra and Hyd agents installed; Hyd may use a sample file | Office IT | Task Scheduler screenshot per site | Pending
GL-07 | Training | HR can drop a file and find failed/ without calling development | HR | Training completion note | Pending
GL-08 | Master Data | Unknown-employee list assigned to named HR owner | HR | Named owner on RAID D-02 | Pending
GL-09 | Rollback | Disable Task Scheduler; previous API git tag documented | Developer | Runbook section with tag name | Pending
GL-10 | Governance | PM + HR written go / no-go on 29 Sep | Project Manager | Email or signed row on this sheet | Pending

## 06_Resource_RACI
Resource Plan and RACI
Who is needed when · hours are estimates for planning, not timesheets
Role | Calendar Days Required | Estimated Hours | Responsibility | RACI — Responsible | RACI — Accountable | RACI — Consulted | RACI — Informed
Developer | D1–D15 (all 15 working days) | 112 | Harden API, scheduler wrapper, package, sit with first site | A1–B2, C1.2 technical | Project Manager | Infra, HR | Office IT
Infra / Server Owner | D1, D3–D5, D8, D14 | 24 | VM, TLS, firewall, backups, DNS | A2.1, A1.2, A1.6, A2.4 | Project Manager | Developer | HR
Office IT (each site) | D9, D11, D12 | 12 | Local Node install and Task Scheduler | B2.2, B3.1, B3.2 | Project Manager | Developer | HR
HR (Noida lead) | D9–D10, D13–D15 | 20 | Drop files, confirm dashboard, unknown-employee list | B2.3, B2.4, C1.1 | Project Manager | Developer | Office IT
HR (Agra / Hyderabad) | D11–D13 | 8 | Repeat drop-folder training | B3.1, B3.2 support | HR Noida lead | Office IT | Project Manager
Project Manager | D1, D13–D15 | 16 | Decisions, RAID, go / no-go, hypercare roster | A0.1, C1.2, C1.3, GL-10 | Sponsor | All roles | Sponsor

## 07_Folder_Contract
Local Folder Contract
Same layout on every office PC · one LOCATION_CODE per machine
Folder Name | Path Convention | Who Writes | Who Reads | Purpose
inbox | <install>\inbox\ | HR | Scheduler | Drop .xls / .xlsx reports here
processing | <install>\processing\ | Scheduler | Scheduler | File moved here while import runs (lock)
processed | <install>\processed\ | Scheduler | IT / HR (audit) | Success archive
failed | <install>\failed\ | Scheduler | HR / IT | Parse or API failure; do not retry forever
logs | <install>\logs\importer.log | Scheduler | IT | Rolling operational log

## 08_Acceptance_Checks
Acceptance Checks
Server pack on 16 Sep · Scheduler pack during Noida soak 22–23 Sep
Check ID | Workstream | Check Name | Pass Rule | Status | Tested Date | Tester Name
SA-01 | A — Central Server | /health | HTTP 200 from inside the VPC and from one office PC | Pending
SA-02 | A — Central Server | UI / | Loads over HTTPS; location filter still works | Pending
SA-03 | A — Central Server | POST /api/attendance/import | Bearer + location header accepted; 401 without token | Pending
SA-04 | A — Central Server | PostgreSQL persist | New batch visible in att_import_batches and att_attendance | Pending
SA-05 | A — Central Server | Idempotency | Second POST of same file updates rows; count unchanged | Pending
SB-01 | B — Local Scheduler | Empty inbox | Exit code 0; INFO log; Task Scheduler shows Success | Pending
SB-02 | B — Local Scheduler | Locked Excel skip | Open file skipped; imported on next tick after close | Pending
SB-03 | B — Local Scheduler | Single instance | Overlapping tick does not double-import | Pending
SB-04 | B — Local Scheduler | Noida 10-minute SLA | Dropped file visible on dashboard within 10 minutes | Pending
SB-05 | B — Local Scheduler | Location tagging | Agra file does not appear as Noida | Pending